## ThiriLwin
No | Descriptions | Reported By | Date Reported | Status | Date Resolved | RootCause
For Assignment
1 | Select the first dealer term (SFR) from dropdownlist , error (An item with the same key has already been added.) has occurred. | ThetSu | 20110921 | KIV |  | When retrieve dealer code, dealer code is same and dictionary got error .(Duplicate Dealer Code)
2 | In dropdownlist , when select some record, can't show properly. (If the desired record is selected from DDL,but show the other data record)-User select team name no including *, it show the above record including * | ThetSu | 20110921 | KIV |  | Duplicate Team Code
3 | If the cheked box is checked , the text box should be enabled. So far all text box fields are enabled . | ThetSu | 20110921 | Done | Sep 24 2011 | After Save Assignment Success, will clear search data.
4 | Email can not send properly. | ThetSu | 20110921 | KIV |  | Vista SMTP Problem
5 | When user change the team from the dropdow list , (From , To , CutOff )date values should be reset. | ThetSu | 20110922 | Closed | Sep 24 2011 | Same with Phase II
6 | In assigned to column,user not selected the Assign dealer.So , the program cann't save this project. But next time , the assign dealer to this project , cann't used this projectname. Show this message 'Project Name Already Exists in System.' | ThetSu | 20110922 | Done | Sep 24 2011 | Logic : (1) When PageLoad, Initialize AccountSetting. (2) If choose Account Type, First ,ClearAllFiled.Second, Apply rules according to webservice. (3) After Search Click, no change. (4) After save Assignment success, InitializeAccount Setting.
7 | The record can't be save the dealer assign to DDL and Project Name text box is reset. | ThetSu | 20110922 | Done | Sep 24 2011
8 | The text box should be clear when pageload again. | ThetSu | 20110922 | Done | Sep 24 2011 | After Save Assignment Click, will clear search data.
9 | If the record is more than 3000, Page cannot load properly. | Thiri | 20110923 | KIV
10 | When user Save Assignment for multiple assignment, the error "Error in Saving Client Assignment". However the Project is saved successful. Then the project name can't be used again to Save Assignment again. Please see the screenshot with No(10) | THA | 20111005 | ERROR |  | Error in Saving Assignment. But there is no rollback for saving project name.
For Contact Entry
1 | Sent Promotion Email pop up , the email from system ddl have 'no record found ' is repeatly. | ThetSu | 20110922 | Done | Sep 27 2011
2 | When user click the "contact history modify" button, Only get the data from "entry history table". | ThetSu | 20110922 | KIV | Sep 27 2011 | Same with Phase II
3 | In thte contact history , if delete the record 'There is no row at position 11' error is occurred and 2 rows are deleted. | ThetSu | 20110922 | Error
4 | To update the contact data in first time. "A field or property with the name 'AECode' was not found on the selected data source." errir occurred. | ThetSu | 20110926 | Done | Sep 27 2011 | Add 2 rows(AECode, ALtAECode) under dtEntryHistory
5 | To update the contact data in first time. "A field or property with the name 'AECode' was not found on the selected data source." errir occurred. | ThetSu | 20110926 | Done | Sep 27 2011 | Remove the data binding coding to Contact Entry Form
6 | if the record from client assign to fill the information to the client assign .To update the data , click the link of acc no, the ADD button and click it the error is occurred. | ThetSu | 20110926 | Done | Sep 27 2011 | Remove the data binding coding to Contact Entry Form
9 | To update the client assign data. Error occurred. | ThetSu | 20110926 | Done | Sep 27 2011 | Remove the data binding coding to Contact Entry Form
10 | click the entry history,error occurred | ThetSu | 20110926 | Done | Sep 27 2011 | Remove the data binding coding to Contact Entry Form
11 | Contact Entry Project Must be related project with Client. ProjectType [ C ] | Thiri | Sep 26 2011 | Done | Sep 27 2011
12 | RetrieveDealerEmailByDealerCode //For TE To check Query | Thiri | Sep 26 2011 | Done | Sep 27 2011
13 | Contact Entry , When client click the Entry History , It's show the data in entry form. Remarks : comment the coding binding data to entry form . | Thiri | Sep 26 2011 | Done | Sep 27 2011
14 | Column 'SeminarName' does not belong to table dtContactHistory. if (lastAcctNo.Equals(acctNo)) Called =>clientContactDA. InsertClientContact Action: Add new row For (a) Seminar Name , FollowUpStatus, FollowUpDate | Thiri | Sep 26 2011 | Done | Sep 27 2011
15 | Contact Entry Email Format Wrong form (html to html) | Thiri | Sep 26 2011 | Done | Sep 30 2011
16 | Project Objective | Thiri | Sep 28 2011 | Done | Sep 30 2011
17 | Storeprocedure for Prepare Contact Entry (a)RetrieveAllDealer (same with phase II) (b) RetrieveContactEntryProjectInfo (ProjectType='C') © RetrieveDealerByUserId (same with phase II) (d)RetrievePreferenceCodeAndName (e) RetrieveUnContactedAssignment (d)RetrieveContactEntryForToday | Thiri | Sep 28 2011 |  | Done
18 | Summary : Contact Entry Admin (1) PageLoad => Only show Dealer List And Project List (2) Selected project=> Bind Uncontact Assignment
For DTSRemainderEmail
1 | Method One Step 1 : Query based on ProjectID . If dealer added the extra call from Contact Entry , data cannot include in calculation. Step 2: FollowUpCall and CallLeft Login could be wrong | Thiri | Sep 26 2011 | KIV
2 | Method Two Step 1 : Step 2: FollowUpCall and CallLeft Login could be wrong | Thiri | Sep 26 2011 | KIV
3 | Contact Entry Query Current ( ModifiedUser=AECode) Logic : Modifed User And AECode is different , current logic wrong . | Thiri | Sep 29 2011 | KIV
4 | SentEmailToContact.aspx Need to add ( Aecode ) | Thiri | Sep 30 2011 | Done | Sep 30 2011
5 | SentEmailToContact => ProjectList (Must be only ProjectType"C") | Thiri | Sep 30 2011 | Done | Sep 30 2011
5 | To check Storeprcedure ISNULL value | Thiri | Sep 26 2011 | Done
TO DO LIST
1 | UI Standardization (a) Project Name (b) Alignment © Error Messages
2 | New Module (a) Contact Entry Cross Dealer Team (b) Client Overview retrieve 3 months client data and to show chart on mouse over click (MMF) =Assigned To THA
3 | Assignment short key function
4 | Assignment Remarks Insert Assignmet => Insert with Project ID Update Assignment => Update Existing Record (LastAssignDealer, AcctNo,AND AssignDate )( not insert new ProjectID) | Thiri | Sep 29 2011 | Done | Sep 29 2011 | Comfirmed
5 | Contact Entry Remarks When user key in manually from contact entry form , it will be add without projectID. | Thiri | Sep 29 2011 | Done | Sep 29 2011 | Comfirmed
6 | GetDearlerEmailByDealerID RefMonthYear + DealerID => To change Storeprocedure | Thiri | Sep 29 2011 | Done | Sep 29 2011
8 | Email Attachments | Thiri | Sep 29 2011 | Done | Sep 30 2011
9 | Promotion Email Upload IE Error | Thiri | Sep 29 2011 | Done | Sep 29 2011 | Put Web.config <httpRuntime executionTimeout="240" maxRequestLength="20480" /> If user upload email template , will sent notify email to user.IF there's no email template, notify email wouldn't sent to user.

## ThetSu
No | Descriptions | Reported By | Date Reported | Status | Date Resolved | Remarks
Assigned Client Info
1 | If user didn't choose the project name , should show "please choose project name". | Thiri | 2011-09-23 | KIV
2 | SearchByProject Searching retrieve all the informaion based on the character on wildcard. | Thiri | 2011-10-03 | KIV
Call Report
1 | IF Retrieve with Project Name => Disable AssignDateFrom IF Retrieve with AssignDate => Disable ProjectName | Thiri | 2011-09-23 | Done
2 | RetrieveCallReport (a) RetrieveCallReport(string assignDate) (To change Query ) (b)RetrieveCallReportByLeadProject © RetrieveCallReportByProject | Thiri | 2011-09-23 | KIV
3 | RetrieveFollowUpDateByProjectID To change constant "TA_CQ" | Thiri | 2011-09-23 | Done | Sep 26 2011
4 | Contact History (a)Excel=> with assin date ( Excel Row Error) (b) RetrieveContactHistoryByCriteria (a)RetrieveContactHistoryByClientProjName (b)RetrieveContactHistoryByLeadProjName Remark: (1)Default contactHistoryWIth Lead, should filter. (2) Lead contact should have Remarks , Rank ,PreferA ,Prefer B ,or should change Column Field | Thiri | 2011-09-23 | KIV
Assignment History
Client Analysis
Contact Analysis
1 | How can we define Modified user ? cqDemo1 OR CC.ModifiedUser AS DealerCode ?? Ref:RetrieveContactAnalysis
2