## ThiriLwin
No | Descriptions | Reported By | Date Reported | Status | Date Resolved | RootCause
For Assignment
1 | Select the first dealer term (SFR) from dropdownlist , error (An item with the same key has already been added.) has occurred. | ThetSu | 20110921 | Done |  | When retrieve dealer code, dealer code is same and dictionary got error .(Duplicate Dealer Code)
2 | In dropdownlist , when select some record, can't show properly. (If the desired record is selected from DDL,but show the other data record)-User select team name no including *, it show the above record including * | ThetSu | 20110921 | Closed |  | Duplicate Team Code
3 | If the cheked box is checked , the text box should be enabled. So far all text box fields are enabled . | ThetSu | 20110921 | Done | Sep 24 2011 | After Save Assignment Success, will clear search data.
4 | Email can not send properly. | ThetSu | 20110921 | Closed |  | Vista SMTP Problem
5 | When user change the team from the dropdow list , (From , To , CutOff )date values should be reset. | ThetSu | 20110922 | Closed | Sep 24 2011 | Same with Phase II
6 | In assigned to column,user not selected the Assign dealer.So , the program cann't save this project. But next time , the assign dealer to this project , cann't used this projectname. Show this message 'Project Name Already Exists in System.' | ThetSu | 20110922 | Closed | Sep 24 2011 | Logic : (1) When PageLoad, Initialize AccountSetting. (2) If choose Account Type, First ,ClearAllFiled.Second, Apply rules according to webservice. (3) After Search Click, no change. (4) After save Assignment success, InitializeAccount Setting.
7 | The record can't be save the dealer assign to DDL and Project Name text box is reset. | ThetSu | 20110922 | Done | Sep 24 2011
8 | The text box should be clear when pageload again. | ThetSu | 20110922 | Done | Sep 24 2011 | After Save Assignment Click, will clear search data.
For Contact Entry
1 | Sent Promotion Email pop up , the email from system ddl have 'no record found ' is repeatly. | ThetSu | 20110922 | Done | Sep 27 2011
2 | When user click the "contact history modify" button, Only get the data from "entry history table". | ThetSu | 20110922 | KIV | Sep 27 2011 | Same with Phase II
3
4 | To update the contact data in first time. "A field or property with the name 'AECode' was not found on the selected data source." errir occurred. | ThetSu | 20110926 | Done | Sep 27 2011 | Add 2 rows(AECode, ALtAECode) under dtEntryHistory
5 | To update the contact data in first time. "A field or property with the name 'AECode' was not found on the selected data source." errir occurred. | ThetSu | 20110926 | Done | Sep 27 2011 | Remove the data binding coding to Contact Entry Form
6 | if the record from client assign to fill the information to the client assign .To update the data , click the link of acc no, the ADD button and click it the error is occurred. | ThetSu | 20110926 | Done | Sep 27 2011 | Remove the data binding coding to Contact Entry Form
9 | To update the client assign data. Error occurred. | ThetSu | 20110926 | Done | Sep 27 2011 | Remove the data binding coding to Contact Entry Form
10 | click the entry history,error occurred | ThetSu | 20110926 | Done | Sep 27 2011 | Remove the data binding coding to Contact Entry Form
11 | Contact Entry Project Must be related project with Client. ProjectType [ C ] | Thiri | Sep 26 2011 | Done | Sep 27 2011
12 | RetrieveDealerEmailByDealerCode //For TE To check Query | Thiri | Sep 26 2011 | Done | Sep 27 2011
13 | Contact Entry , When client click the Entry History , It's show the data in entry form. Remarks : comment the coding binding data to entry form . | Thiri | Sep 26 2011 | Done | Sep 27 2011
14 | Column 'SeminarName' does not belong to table dtContactHistory. if (lastAcctNo.Equals(acctNo)) Called =>clientContactDA. InsertClientContact Action: Add new row For (a) Seminar Name , FollowUpStatus, FollowUpDate | Thiri | Sep 26 2011 | Done | Sep 27 2011
15 | Contact Entry Email Format Wrong form (html to html) | Thiri | Sep 26 2011 | Done | Sep 30 2011
16 | Project Objective | Thiri | Sep 28 2011 | Done | Sep 30 2011
17 | Storeprocedure for Prepare Contact Entry (a)RetrieveAllDealer (same with phase II) (b) RetrieveContactEntryProjectInfo (ProjectType='C') © RetrieveDealerByUserId (same with phase II) (d)RetrievePreferenceCodeAndName (e) RetrieveUnContactedAssignment (d)RetrieveContactEntryForToday | Thiri | Sep 28 2011 |  | Done
18 | Summary : Contact Entry Admin (1) PageLoad => Only show Dealer List And Project List (2) Selected project=> Bind Uncontact Assignment
For DTSRemainderEmail
1 | Method One Step 1 : Query based on ProjectID . If dealer added the extra call from Contact Entry , data cannot include in calculation. Step 2: FollowUpCall and CallLeft Login could be wrong | Thiri | Sep 26 2011 | Closed |  | AssignToTHA
2 | Method Two Step 1 : Step 2: FollowUpCall and CallLeft Login could be wrong | Thiri | Sep 26 2011 | Closed |  | AssignToTHA
3 | Contact Entry Query Current ( ModifiedUser=AECode) Logic : Modifed User And AECode is different , current logic wrong . | Thiri | Sep 29 2011 | Closed |  | AssignToTHA
4 | SentEmailToContact.aspx Need to add ( Aecode ) | Thiri | Sep 30 2011 | Done | Sep 30 2011
5 | SentEmailToContact => ProjectList (Must be only ProjectType"C") | Thiri | Sep 30 2011 | Done | Sep 30 2011
5 | To check Storeprcedure ISNULL value | Thiri | Sep 26 2011 | Done
TO DO LIST
1 | UI Standardization (a) Project Name (b) Alignment © Error Messages
2 | New Module (a) Contact Entry Cross Dealer Team (b) Client Overview retrieve 3 months client data and to show chart on mouse over click (MMF) =Assigned To THA
3 | Assignment short key function
4 | Assignment Remarks Insert Assignmet => Insert with Project ID Update Assignment => Update Existing Record (LastAssignDealer, AcctNo,AND AssignDate )( not insert new ProjectID) | Thiri | Sep 29 2011 | Done | Sep 29 2011 | Comfirmed
5 | Contact Entry Remarks When user key in manually from contact entry form , it will be add without projectID. | Thiri | Sep 29 2011 | Done | Sep 29 2011 | Comfirmed
6 | GetDearlerEmailByDealerID RefMonthYear + DealerID => To change Storeprocedure | Thiri | Sep 29 2011 | Done | Sep 29 2011
8 | Email Attachments | Thiri | Sep 29 2011 | Done | Sep 30 2011
9 | Promotion Email Upload IE Error | Thiri | Sep 29 2011 | Done | Sep 29 2011 | Put Web.config <httpRuntime executionTimeout="240" maxRequestLength="20480" /> If user upload email template , will sent notify email to user.IF there's no email template, notify email wouldn't sent to user.
20111010_Error List
1 | If the record is more than 3000,Assignment page cannot show properly. | Thiri | 20110923 | KIV
2 | In thte contact history , if delete the record 'There is no row at position 11' error is occurred and 2 rows are deleted. | ThetSu | 20110922 | Error
3 | Error is occurred save the assign after one time ProjectNameAlreadyExist show. | Thiri |  | Major Changes |  | First Time, Grid can't show the updated data properly. So when the assignment save next time,error occur when duplicated record insert to data base.
4 | Need to check the places using "OR" operator | Thiri |  | To Check
5 | trustAccFlag / MMFFlag MMF (OR ) AUM ?? |  |  | To Check
6 | contHisFlag |  |  | To Check
7 | To remove testing data
8 | Updating Assignment will go to old assignment or new assignment. |  |  | Major Changes

## ThetSu
No | Descriptions | Reported By | Date Reported | Status | Date Resolved | Remarks
Assigned Client Info
1 | If user didn't choose the project name , should show "please choose project name". | Thiri | 2011-09-23 | KIV
2 | Pagination: -User can navigate from one page to another page if the client records retrieval can not be displayed in on screen. User can go to the specified page, first page, last page, previous page and next page. User can specify the number of records per page | Thiri | 2011-10-05 | To Test
3 | SearchByProject Searching retrieve all the informaion based on the character on wildcard. | Thiri | 2011-10-03 | KIV
Call Report
1 | IF Retrieve with Project Name => Disable AssignDateFrom IF Retrieve with AssignDate => Disable ProjectName | Thiri | 2011-09-23 | Done
2 | RetrieveCallReport (a) RetrieveCallReport(string assignDate) (To change Query ) (b)RetrieveCallReportByLeadProject © RetrieveCallReportByProject | Thiri | 2011-09-23 | KIV
3 | RetrieveFollowUpDateByProjectID To change constant "TA_CQ" | Thiri | 2011-09-23 | Done | Sep 26 2011
4 | Contact History (a)Excel=> with assin date ( Excel Row Error) (b) RetrieveContactHistoryByCriteria (a)RetrieveContactHistoryByClientProjName (b)RetrieveContactHistoryByLeadProjName Remark: (1)Default contactHistoryWIth Lead, should filter. (2) Lead contact should have Remarks , Rank ,PreferA ,Prefer B ,or should change Column Field | Thiri | 2011-09-23 | KIV
5 | System will retrieve the matched individual Dealer's Call by displaying No of Miss Called, No of Extra Call, No of Retrade Count after Assignments, No of Retrade Count after Extra Call and Score for dealer. If no record is found, the system will display "Call Report not Found!" | Thiri | 2011-10-05 | To Test
6 | Pagination: -User can navigate from one page to another page if the client records retrieval can not be displayed in on screen. User can go to the specified page, first page, last page, previous page and next page. User can specify the number of records per page | Thiri | 2011-10-05 | To Test
Assignment History
| Pagination: -User can navigate from one page to another page if the client records retrieval can not be displayed in on screen. User can go to the specified page, first page, last page, previous page and next page. User can specify the number of records per page |  |  | To Test
Client Analysis
Contact Analysis
1 | How can we define Modified user ? cqDemo1 OR CC.ModifiedUser AS DealerCode ?? Ref:RetrieveContactAnalysis
2 | Contact Analysis RetrieveByProject

## YinMonWin
No | Descriptions | Status | Reported By | Date Reported | Status | Date Resolved | RootCause
For Lead Data
Key in case
1 | When click the header link of the grid view , the gridview fired event sorting error is occurred. |  | Thet Su
2 | * key row should not be blank. But don't fill up this row and can save it. In both update case. |  | Thet Su
3 | In save case , I don't select the Gender but It save automically Male. |  | Thet Su
Upload case
1 | Page link can't be used. The error is occurred. |  | Thet Su
5 | If delete the row , the grid view is disappeared and can't delete the row. If the data row is in the LeadArchive, occurred this case. |  | Thet Su
6 | When user clicks the submit button with Duplicate Records, should show the information " Please comfirm the duplicate Records". At the same time, should hide the "Leads record is inserted successfully." From KeyIn Tab. |  | Thiri | 2011-05-10
7 | When user clicks the Details for each lead records, If there is no data , unneccessary data rows should be remove form uploaded Record table . |  | Thiri | 2011-05-10
8 | There is no way to comfirm upload data is successful or not since the message always show update successful. |  | Thiri | 2011-05-10
9 | Need to check Email Format for Key In Form |  | Thiri | 2011-05-10
10 | Need to check Validation Name |  | Thiri | 2011-05-10
11 | Need to check Validation Mobile Number |  | Thiri | 2011-05-10
12 | Leads already exists! Based On Mobile Number |  | Thiri | 2011-05-10
For Lead Assign
1 | User select the team 10 but I may be the above team name. |  | Thet Su
2 | Save assign and delete one row. But the gird and the assign table don't match. |  | Thet Su
3 | To modify the record , click the leadid link the errror is occurred and it add the db as new record. |  | Thet Su
4 | Don’t type the project name , can’t find the clients list. It should not be. Need to remove the requirement validation for ProjectName in search function. |  | Thet Su
5 | when not yet assign , it is different with client assign , as delete button |  | Thet Su
6 | Select Team SFR didn't work properly. |  | Thiri | 2011-05-10
7

## Additional Request
DealerManagement Form Changes
No | Current Fun | Changes with additional Email
1 | Search Function Show Search Data | Done
2 | Add Function | Done
3 | Update | Done
4 | Cancel | Done
5 | Show Form | Done
6 | Modified Click Event | DisplayDetails() Need to add CellValue
Email Form Changes
No | Module | Function | Result
1 | Assignment | SentEmailToDealer (SPM -> Dealer ) SentPromotionLetterToClient (TeamEmail-> Client)
| TO DO LIST | Status
1 | RetrieveTeamEmailByTeamCode
2 | ContactEntryAdmin If Supervisor role is admin, RetriveAllDealer | RetrieveAllProject (no need cross team)
3 | Check Email Teamplate | Done
4 | To change constant value from EmailManager and ClientAssign | Done
5 | ddlActualDealer Drop DownList functions | Closed(AssignedTo THA)
6 | After Email Template upload to client assignment , can upload the attachment files. | Done
7 | Email Logo At Client Assignment | Done
8 | Email paging At Email Template | Closed
9 | System should not allow user to add attached files if user didn't upload the email template | Done
10 | After Auto Assign removed, auto assign table still showing | Done
11 | To create folder to save logo in source code folder and show logo when email send out | Done
12 | PromotionEmailFromAssignment /ContactEntry | Done
Testing 20111008
1 | lstAccountTypes_SelectedIndexChanged | OK
1 | Email Character Replacement | Ok
3 | EmailFormat in functions | Ok
5 | Error in insert dealer with SFR userid= ittest | Ok
7 | Email Template To check the email template name already exists or not. | Done
No | Module | Function
1 | Assigment | SentPromotionEmailToClient
2 | Assigment | SentAnnouncementEmailToDealer
3 | DTSCallReport | SentRemainderEmailToDealer
4 | DTSCallReport | SentRemainderEmailToDealer
5 | ContactEntry | SentPromotionEmailToClient
6 | ContactEntry | SentFollowUpEmailToClient

## PNP Deleted
210 | Whistle Blowing Policy Version 1.0 | <p><a href="http://corpportal-svr/CNPFiles/Images/ArticleImages/Whistle Blowing Policy Version 1.0.pdf ">Whistle Blowing Policy Version 1.0</a></p> | 2 | 12 | 0 | 40073.7704 | whistle-blowing-policy-version-1-0 | 16 | Whistle Blowing Policy Version 1.0 | 0 | NULL | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NULL | 0 | 0 | 0 | 0 | 0